## Product Backlog
UC17: Enterprise Human Capital Management Data Platform (EHCMDP)
Digital Assignment 1 – Sprint 0, Sprint 1 & Sprint 2
Description
ID | Backlog Item / Work |  | Sprint | Expected Deliverable | Assigned To
1 | Profile Workforce Datasets Using Python/Pandas | Profile Sprint 1 staging datasets: dimensions, data types, nulls, unique values, duplicates and descriptive statistics. | Sprint 2 | Data Profiling Report | Likisha
2 | Perform EDA and Statistical Analysis | Perform relevant exploratory analysis and descriptive statistics to support data-quality and warehouse decisions. | Sprint 2 | EDA / Analysis Evidence | Likisha
3 | Analyze Data Quality Issues | Identify duplicate employee records, missing payroll information, inconsistent attendance records and incomplete recruitment data using profiling evidence. | Sprint 2 | Data Quality Findings | Madhumitha
4 | Clean and Standardize Employee and Organizational Data | Apply profiling-driven rules to clean and standardize employee and organizational master data. | Sprint 2 | Cleaned and Standardized Data | Madhumitha
5 | Validate Cleaning and Data Quality Results | Validate before/after results against defined quality rules and document unresolved issues. | Sprint 2 | Data Quality Validation Evidence | Madhumitha
6 | Design EHCMDP Star Schema | Define grain, fact and dimension tables, keys, relationships and workforce measures from validated data. | Sprint 2 | Star Schema | Ankita, Likisha
7 | Create PostgreSQL Warehouse Dimensions | Implement and populate approved dimension tables with appropriate keys, attributes and data types. | Sprint 2 | Warehouse Dimensions | Ankita
8 | Create PostgreSQL Warehouse Facts | Implement and populate required fact tables from validated and standardized data. | Sprint 2 | PostgreSQL Data Warehouse | Ankita
9 | Develop SQL Workforce Reporting Scripts | Develop and validate workforce reporting and retrieval queries against the PostgreSQL warehouse. | Sprint 2 | SQL Scripts | Likisha
10 | Prepare Sprint 2 Data Quality Documentation | Consolidate quality findings, cleaning rules, treatment decisions and validation evidence into the Data Quality Report. | Sprint 2 | Data Quality Report | Madhumitha, Likisha
11 | Prepare Star Schema and Warehouse Documentation | Document the approved Star Schema and implementation decisions so the design is traceable to the warehouse. | Sprint 2 | Star Schema / Warehouse Documentation | Ankita
TR-01 | tr_employee_performance_ingestion.ktr | Pentaho Ingestion Transformation | Likisha
TR-02 | Human_Resource_CSV_Ingestion.ktr | Pentaho Ingestion Transformation | Likisha
TR-03 | HR_Employee_CSV_Ingestion.ktr | Pentaho Ingestion Transformation | Likisha
TR-04 | AI_Fair_Recruitment_JSON_Ingestion.ktr | Pentaho Ingestion Transformation | Likisha
TR-05 | Payroll_Data_Ingestion.ktr | Pentaho Ingestion Transformation | Likisha
TR-06 | Employee_Attendance_XML_Ingestion.ktr | Pentaho Ingestion Transformation | Madhumitha
TR-07 | Employee_Leave_CSV_Ingestion.ktr | Pentaho Ingestion Transformation | Madhumitha
TR-08 | HR_Performance_Rating_CSV_Ingestion.ktr | Pentaho Ingestion Transformation | Madhumitha
TR-09 | Amazon_Employee_Access_JSON_Ingestion.ktr | Pentaho Ingestion Transformation | Madhumitha
TR-10 | HR_SaaS_Employee_Master_Excel_Ingestion.ktr | Pentaho Ingestion Transformation | Madhumitha
TR-11 | HR_SaaS_Employee_Snapshot_XML_Ingestion.ktr | Pentaho Ingestion Transformation | Ankita
TR-12 | HR_SaaS_Leave_Request_JSON_Ingestion.ktr | Pentaho Ingestion Transformation | Ankita
TR-13 | Employee_Performance_Audio_Excel_Ingestion.ktr | Pentaho Ingestion Transformation | Ankita
TR-14 | Employee_Performance_Behavior_JSON_Ingestion.ktr | Pentaho Ingestion Transformation | Ankita
TR-15 | Employee_Performance_Structured_XML_Ingestion.ktr | Pentaho Ingestion Transformation | Ankita

## Sprint 2 Allocation
Member | Connected Primary Work | Sprint 2 Outputs | Transformation Allocation
Likisha | Python/Pandas profiling → EDA/statistics → SQL reporting → profiling documentation | Data Profiling Report; EDA evidence; SQL Scripts | 5 transformations
Madhumitha | Data quality analysis → cleaning/standardization → validation → Data Quality Report | Data Quality Report; cleaned/standardized data; validation evidence | 5 transformations
Ankita | Star Schema → warehouse dimensions → warehouse facts → schema/warehouse documentation | Star Schema; PostgreSQL Data Warehouse | 5 transformations
All Three | Cross-review → end-to-end reconciliation → final documentation and Git integration | Integrated validation; final Sprint 2 deliverables; Git updates | Joint responsibility
Balance Principle | Each member owns one complete technical workstream of comparable importance. Shared work is limited to activities that genuinely require all three.

## Transformation Allocation
Group | Member | Transformation
Group A | Likisha | tr_employee_performance_ingestion.ktr
Group A | Likisha | Human_Resource_CSV_Ingestion.ktr
Group A | Likisha | HR_Employee_CSV_Ingestion.ktr
Group A | Likisha | AI_Fair_Recruitment_JSON_Ingestion.ktr
Group A | Likisha | Payroll_Data_Ingestion.ktr
Group B | Madhumitha | Employee_Attendance_XML_Ingestion.ktr
Group B | Madhumitha | Employee_Leave_CSV_Ingestion.ktr
Group B | Madhumitha | HR_Performance_Rating_CSV_Ingestion.ktr
Group B | Madhumitha | Amazon_Employee_Access_JSON_Ingestion.ktr
Group B | Madhumitha | HR_SaaS_Employee_Master_Excel_Ingestion.ktr
Group C | Ankita | HR_SaaS_Employee_Snapshot_XML_Ingestion.ktr
Group C | Ankita | HR_SaaS_Leave_Request_JSON_Ingestion.ktr
Group C | Ankita | Employee_Performance_Audio_Excel_Ingestion.ktr
Group C | Ankita | Employee_Performance_Behavior_JSON_Ingestion.ktr
Group C | Ankita | Employee_Performance_Structured_XML_Ingestion.ktr